## Sheet1
Action Plan Priority Item--2018 Rankings | Progress-2019 | Funding Potential: Source(s)
1.Advance projects which Increase in-stream flows esp. in the summer months (i.e. off-stream water storage with summer forbearance, acquisition and 1707 dedication of current summer riparian diversions) | Significant: Rancho Canada Acquisition and 1707 Dedication; CRTF researching forbearance prospects | High: Prop. 1 and CAW Settlement
2.Develop an adaptive management program for water quantity and quality in the CR Lagoon | At Risk: CR Lagoon EIR in final stages but project on hold due to budget reductions | High: Prop. 1, CSA-1, and St Pks Coastal Erosion Program
3.Control non-native vegetation and invasive species (especially striped bass) in watershed | Still in infancy; investigating instream rremoval of invasive species | Low: no funding source identified as yet except CDFW (striped bass)
4.Remove fish passage barriers in CR and tributaries | Significant: TU’s grants for three creeks approved and work underway | High: FRGP and CAW Settlement
5.Restore problematic riparian areas | Significant: MPWMD annual riparian restoration program | Moderate: mitigation funds
6.Support the Carmel River FREE Project | Still showing funding shortfall but FEMA grant may close the funding gap | High: Still seeking add’l funding
7.Add anchored large woody debris to river channel | Significant: at Dampierre Park, South Arm, and Lower Mainstem | High: Prop. 1 and CAW Settlement
8.Establish a sediment transport modeling program below former SC Dam site | Significant: CSUMB and MPWMD conducting annual particle studies; sediment transport model developed for Los Padres Dam analysis; need sediment transport measurements | Funded by CAW and MPWMD
9.Tag and monitor passage of steelhead | Significant: NOAA Science Center/MPWMD Tagging program in mainstem and tributaries and arrays being installed | High: CAW Settlement and Prop. 1; CDFW’s FRGP; Sleepy Hollow Rearing Facility tagging planned
10.Evaluate future of Los Padres Dam | Significant: the MPWMD alternatives analysis underway but has delays | High: funding already secured
11.Augment gravel in river channel | Significant: MPWMD injections and 2017-2019 flood effects; planned project in 2019 | High: mitigation funds, CAW Settlement
12.Create and fund a volunteer coordinator role and expand volunteer activities | Still in embryonic stage except for separate agencies’ programs | Low: no funding source identified except agency contributions