## Sheet1
Action Plan Priority Item--Most Recent Ranking | Progress--September 2021 | Funding Potential: Source(s)
1.Advance projects which Increase in-stream flows esp. in the summer months (i.e. off-stream water storage with summer forbearance, acquisition and 1707 dedication of current summer riparian diversions) | Significant: Rancho Canada Acquisition and 1707 Dedication; CRTF researching forbearance prospects with MPWMD, CRSA, and TU. Committee formed to research potential forbearance agreements met three times by Zoom. Committee members met with forbearance or recycling prospects. CAWD in process to annex more of Carmel Valley wastewater sources that would send the recycled water to Pebble Beach. This may negatively impact streamflow by eliminating percolating domestic wastewater, but should benefit water quality by reducing the number of septic tanks in the valley. Will meet with Reclamation Authority to discuss retaining some Carmel Valley recycled wastewater in the CR watershed. Researching expansion of the Carmel Valley Ranch treatment facility. | High: Prop. 1, WCB Stream Flow Grant and CAW Settlement Funds
2.Develop an adaptive management program for water quantity and quality in the CR Lagoon; complete Lagoon and SRPS Revised EIR | Restarted: CR Lagoon EIR process re-started due to $450k funding approved by BOS and $100k provided by CSA-1. Shandy Carroll leading this EIR revision; periodic updates released including a task timeline. Technical Advisory Committee formed and has reviewed three technical studies. CSA-1 continues to provide input re SRPS. Urgency has increased due to recent flooding on north side of Lagoon, when sand bar management failed to prevent flooding. EPB on the property lines still under consideration. | High: County Budget Augmentation; Prop. 1, CSA-1 ($100k), and St Pks Coastal Erosion Program after Revised EIR is certified
3.Control non-native vegetation and invasive species (especially striped bass, NZ mussels, genista and eucalyptus) in watershed | Embryonic: Genista removal begun by CVA; investigating instream removal of invasive species esp. striped bass and NZ mussels | Low: few funding sources identified except CVA, CRWC, and CRSA and CDFW (striped bass)
4.Remove fish passage barriers in CR and tributaries; conduct a watershed-wide evaluation of remaining fish passage barriers | Significant: TU’s and MCRCD's grants for four creeks (Cachagua, Finch, San Clemente, Potrero) approved and design and removal/reconstruction work underway; New bridge completed at SC Creek; MPWMD and TU monitoring sites at risk esp. concrete blockage near CAWD facility that SCC contributed funds to assess and potentially modify. | High: CDFW's FRGP and CAW Settlement
5.Restore problematic riparian areas | Significant: MPWMD annual riparian restoration program; Former Rancho Canada site being restored by MPRPD grant to SCC/MCRCD; many volunteers participating in MPRPD replantings. | Moderate: mitigation funds and MPRPD funding
6.Support the Carmel River FREE Project | Promising: EIR completed and BOS to consider certification on 4/11. FEMA and other grants likely to close the funding gap. Close to a decision re final budget. | High: FEMA grant looks increasingly likely; applied for DWR $5m grant
7.Add anchored large woody debris to river channel | Significant: at Dampierre Park, South Arm, and Lower Mainstem (Carmel River Steelhead Association project). No other projects underway at this time. | High: Prop. 1 and CAW Settlement
8.Establish a sediment transport modeling program below former SC Dam site (now part of Lagoon/SRPS EIR Revision project) | Significant: CSUMB and MPWMD conducting annual particle studies; sediment transport model developed for Los Padres Dam analysis; lower river sediment transport study being conducted by NPS's Mara Orescanin as part of EIR technical studies funded by County and CSA-1 | High: Funded by CAW, RMA, MPWMD
9.Restore steelhead population in the river and streams by sponsoring fish rescues, tagging and monitoring migration of steelhead | Significant: NOAA Science Center/MPWMD Tagging and monitoring program in mainstem and tributaries and arrays installed; CRSA and MPWMD rescued over 20k in 2019 and have conducted fish rescues in summer 2020 yielding 12,182 fish. Sleepy Hollow Facility to be ready in the near future. DNA testing and tracking under consideration. | High: CAW Settlement and Prop. 1; CDFW’s FRGP; Sleepy Hollow Rearing Facility tagging planned
10.Evaluate future of Los Padres Dam | Significant: the MPWMD alternatives analysis underway but has delays; projected release in 2022-23 | High: funding already secured
11.Augment gravel in river channel | Significant: MPWMD injected over 7000 tons since 1993. 2017-2019 flood effects added gravel to mainstem. This will continue until Los Padres Dam is removed. | High: mitigation funds, CAW Settlement
12. Floodplain acquisition and restoration at former Rancho Canada and similar sites | Significant: Restoration planning by MPRPD at PCRP underway with a TAC; new vision for PCRP completed and contracts issued to McBain & SWCA. | High: MPRPD funds, Trust for Public Lands, mitigation and CAW Settlement funds
13. Manage fuel load in watershed to control wildfire spread in and impacts to watershed | Underway in SLC and MPRPD lands; Fuels Coordinator working on additional grants and establishing six local FireWise communities. Wildfire detection camera network being developed. | High: Fuel Mitigation Coordinator has secured grants and applied for more grants; CRWC offered additional funding support to establish FireWise neighborhoods.
14. Restore threatened CA Red-Legged Frog populations in watershed | Underway due to plantings by USFW in mainstem and local sites; biological opinion issued; new contact for CRLF recovery--Danielle Fagre | Moderate: USFW funding recovery efforts so far